## Manav
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Manav | 8 | 7 | 1 | 1 - requirement analysis 5 - attend group meeting, discuss. ... | 0 | 7 |  |  |  | 1 |  |  | 8
2 | Manav | 10 | 8 | 1 | 1-requirement analysis 5-communication 6-presentation | 4 |  |  |  |  | 1 | 3 | 8
3 | Manav | 14 | 14 | 1 | 2-Design, worked on the UI Framework design. 3 - Implementation, created a reusable framework using Html5, JQuery, RequireJs, Bootstrap, Kendo client libraries 5 - Communication/management, communicating my changes to team. Knowledge transfer of how to use the framework and implementation details. | 0 |  | 2 | 11 |  | 1 |  | 16
4 | Manav | 12 | 11 | 1 | 2 - UI Framework redesign, moved common client functionality to common.js 3 - Developing dashboard page, home page with hard coded data 5 - Communication/management, communicating my changes to team. Knowlwdge transfer of how to use the frame work and implementation details |  |  | 1 | 10 |  | 1
5 | Manav | 14 | 13 | 1 | 2 - Styling of dashboard page, home page. Styling of login page, registration page, manage roles page 5 - Communicatio/management |  |  | 13 |  |  | 1

## Vipul
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Vipul | 7 | 6 | 1 | 1 - requirement analysis 5 - attend group meeting discuss. ... | 0 | 6 |  |  |  | 1 |  |  | 8
2 | Vipul | 11 | 10 | 1 | 0 - learning 1 - requirement analysis 5 - communication/management | 4 | 6 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, create database | 10
3 | Vipul | 12 | 11 | 1 | 0- learning SQL 1 - database design analysis 2 - communication/management 3- database creation | 2 | 2 | 2 | 5 | 0 | 1 | 0 | UI mock ups, polish user stories, create database | 10
4 | Vipul | 14 | 13 | 1 | 2- Database design 3- Learning how to implement the login page 5- Communication that is communicating the progress to the team |  |  | 3 | 9 |  | 1 |  | Database schema. Implementation of the login page and work on the database. Presentation for iteration1 | 15
5 | Vipul | 16 | 14 | 2 | 2- Designed the database schema. 3- Implementation of the login page and worked on the database. 5- Communication/Management that is communicated the progress to the team Also worked on the presentation for iteration1 |  |  | 5 | 8 |  | 1 |  | Review the work done till iteration 1 Check out the work that needs to be done for the next iteration | 20

## Vipul A
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Vipul Aggarwal | 7 | 6 | 1 | 1 - requirement analysis 5 - attend group meeting discuss. ... | 0 | 6 |  |  |  | 1 |  |  | 8
2 | Vipul | 11 | 10 | 1 | 0 - learning 1 - requirement analysis 5 - communication/management | 5 | 5 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, | 10

## Yuvaraj
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Yuvaraj | 7 | 5 | 2 | 1. requirement analysis 2. design 5. attend group meeting, discussion |  | 2 | 5 |  |  |  |  | create account in github, presentation slide preparation, rough draft for the project design | 7
2 | Yuvaraj | 14 | 13 | 1 | 0-learning 2-design 5-communications for SPMP 6-presentation | 7 |  | 3 |  |  | 2 | 2 | begin developing components for task page, bug page and any other reporting pages | 14
3 | Yuvaraj | 18 | 17 | 1 | 0- learning Kendo UI using Kendo tutorials http://docs.kendoui.com/getting-started/web/appearance-styling learning git basics from the following: http://git-scm.com/book/en/Git-Branching https://github.com/heckendorfc/plm/blob/development/documentation/internal/scmp.pdf http://www.youtube.com/watch?v=RDGzF2M-zlo http://www.youtube.com/watch?v=mYjZtU1-u9Y 2 - worked on the UI Framework design(register,task,bug page) 3 - created a reusable framework using Html5, JQuery, Kendo client libraries 5 - Communication/management, communicating my changes to team. | 10 |  | 3 | 3 |  | 2 |  | implementation of registration, task and bug page | 20
4 | Yuvaraj | 16 | 15 | 1 | 3- working on registration UI implementation service setup 5-communication/management, communicating my change to team |  |  |  | 14 |  | 1 |  | service integration, iteration completion requirements | 25
5 | Yuvaraj | 30 | 27 | 3 | 3- Integrating UI with service for Registration 5 - Assisting team with service/UI integration general supplemental meeting Communication/management, communicating my changes to team. |  |  |  | 20 |  | 10

## Rachit
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Rachit | 7 | 5 | 1 | 1. requirement analysis 2. design 5. attend group meeting, discussion |  | 2 | 5 |  |  |  |  | create account in github, create pivotal tracker account, presentation slide preparation, rough draft for the project design | 10
2 | Rachit | 10 | 8 | 1 | 0 – learning about different UI frameworks and basic html. 1 - requirement analysis 2 – design of UML diagrams 5 - communication/management | 4 | 2 | 1 |  |  | 1 |  | UI mockups and User Stories | 15
3 | Rachit | 16 | 15 | 1 | 2-Design, worked on the UI Framework design. 3 – Learning how to implement a reusable framework using Html5, JQuery, RequireJs, Bootstrap, Kendo client libraries 5 - Communication/management, communicating my changes to team. |  |  | 2 | 10 |  | 1 |  | Review of previous week Update weekly report Implementation of Login page | 20
4 | Rachit | 14 | 13 | 1 | 2-Design, worked on the database fields required. 3 – Learning how to implement the login page. 5 - Communication/management, communicating my changes to team. |  |  | 3 | 9 |  | 1 |  | Designing the database schema. Implementation of the login page and work on the database. Presentation for iteration1 | 15
5 | Rachit | 16 | 14 | 2 | 2- Designed the database schema. 3- Implementation of the login page and worked on the database. 5- Communication/Management that is communicated my changes to the team Also worked on the presentation for iteration1 |  |  | 4 | 9 |  | 1 |  | Review iteration 1 Plan the work for the next iteration | 20

## Yanan
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Alan | 5 | 3 | 2 | 1 - requirement analysis, brainstorm project flow 5 - attend group meeting, discuss. ... | 0 | 3 | 0 | 0 | 0 | 2 | 0 | user stories, SPMP | 5
2 | Alan | 11 | 10 | 1 | 0 - learning requirements documentation, what needs to be added to SPMP 1 - requirement analysis 5 - communication/management | 4 | 6 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, update SPMP | 10
3 | Alan | 10 | 9 | 1 | 0 - refresh HTML and related languages 2 - UI Mock Ups based on user stories | 5 | 0 | 3 | 0 | 0 | 1 | 0 | Code iteration 1 user story, itegration with services | 8
4 | Alan | 17 | 14 | 3 | 0 - learning JS, jQuery and JSON 2/3 - Add Role user story design, code 5 - learning environment setup, tutorials | 8 | 0 | 1 | 3 | 0 | 2 | 0 | continue implementation, rewrite SPMP sections, prepare for presentation | 18
5 | Alan | 14 | 13 | 1 | 0 - JQuery/JSON documentation 3 - add Role implementation 4 - Get environment up and running, test commited pages for functionality/behavior 5 - Google Group, emails, presentation duties - check everything 6 - Update/rewrite SPMP | 2 | 0 | 0 | 2 | 2 | 3 | 4 | discuss what needs to be done for iteration 2, design work for new user stories, initial coding | 10

## Christian
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Christian | 14 | 12 | 2 | 1 - requirement analysis 5 - attend group meeting, discuss. ... 6 - plan and set up infrastructure for SCM and software deployments to server | 0 | 2 |  |  |  | 2 | 8 | Set up repo layout, requirement analysis, begin learning technologies. | 12
2 | Christian | 22 | 21 | 1 | 0 - Learning required technologies for development 3 - Implementing reference code for back-end and configuring development server 5 - Communivations for and working on SCMP/SPMP | 6 |  |  | 12 |  | 3 |  | Begin developing services | 14
3 | Christian | 29 | 28 | 1 | 0 - Learning required technologies for development (JPA, JAX-RS) 2 - Developing database schema 3 - Developing authentication and role management services. Implementing JPA code. 4 - Writing test cases for services | 5 |  | 1 | 21 | 1 |  |  | Developing services required for requirements | 20
4 | Christian | 26 | 25 | 1 | 3 - Developing role management, dashboard, and authorization services 4 - Writing test cases for services 5 - Assisting team with service/UI integration |  |  |  | 22 | 1 | 2 |  | Work on service/UI integration, assist with iteration completion requirements (documentation, etc) | 15
5 | Christian | 34 | 31 | 3 | 2 - Writing class diagram for services 3 - Integrating UI with services for login, dashboard, authorization, role management 5 - Assisting team with service/UI integration and general supplemental meeting |  |  | 10 | 18 |  | 6 |  | Work on redesign of the system, implement new services, fix UI issues | 15

## Tandhy
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Tandhy | 9 | 7 | 2 | 5 - group meeting 1 - requirement analysis 0 - learning | 5 | 2 | 0 | 0 | 0 | 2 | 0 | 0 - learning 2 - design 5 - group meeting 6 - work on SQAP | 7
2 | Tandhy | 8 | 8 | 1 | 0 - learning 6 - SQAP documentation | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 - learning 6 - work on testing tools | 10
3 | Tandhy | 8 | 7 | 1 | 0 - learning on selenium, how to install, perform initial test 2 - draft UI Storyboard | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 - learning on UnitTesting and database testing 2 - finish UI Storyboard and work on UI | 10
4 | Tandhy | 12 | 12 | 1 | 0 - learning selenium, particular on how to perform web testing 2 - design storyboard 3 - implement PHP script to retrieve Comment from uploaded File | 2 | 0 | 2 | 8 | 0 | 0 | 0 | 2 - revise storyboard 3 - implement user Story and modify retrieveComment to support folder process 6 - work in SPMP and test documents | 10
5 | Tandhy | 22 | 20 | 2 | 2 - finish use case, state diagram, metric iteration 1, code documentation 3 - implement Java Script to count source code, retrieve comment 4 - testing PLM to retrieve comment and count line of code | 0 | 0 | 6 | 12 | 2 | 0 | 0 | 2 - work on test cases 3 - implement user story, revised java for retrieving comment and LOC | 10