## Manav
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Manav | 8 | 7 | 1 | 1 - requirement analysis 5 - attend group meeting, discuss. ... | 0 | 7 |  |  |  | 1 |  |  | 8
2 | Manav | 10 | 8 | 1 | 1-requirement analysis 5-communication 6-presentation | 4 |  |  |  |  | 1 | 3 | 8

## Vipul
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Vipul | 7 | 6 | 1 | 1 - requirement analysis 5 - attend group meeting discuss. ... | 0 | 6 |  |  |  | 1 |  |  | 8
2 | Vipul | 11 | 10 | 1 | 0 - learning 1 - requirement analysis 5 - communication/management | 4 | 6 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, create database | 10

## Vipul A
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Vipul Aggarwal | 7 | 6 | 1 | 1 - requirement analysis 5 - attend group meeting discuss. ... | 0 | 6 |  |  |  | 1 |  |  | 8
2 | Vipul | 11 | 10 | 1 | 0 - learning 1 - requirement analysis 5 - communication/management | 5 | 5 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, | 10

## Yuvaraj
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Yuvaraj | 7 | 5 | 2 | 1. requirement analysis 2. design 5. attend group meeting, discussion |  | 2 | 5 |  |  |  |  | create account in github, presentation slide preparation, rough draft for the project design | 7
2 | Yuvaraj | 14 | 13 | 1 | 0-learning 2-design 5-communications for SPMP 6-presentation | 7 |  | 3 |  |  | 2 | 2 | begin developing coponents for task page, bug page and any other reporting pages | 14

## Rachit
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Rachit | 7 | 5 | 2 | 1. requirement analysis 2. design 5. attend group meeting, discussion |  | 2 | 5 |  |  |  |  | create account in github, create pivotal tracker account, presentation slide preparation, rough draft for the project design | 7

## Yanan
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Alan | 5 | 3 | 2 | 1 - requirement analysis 5 - attend group meeting, discuss. ... | 0 | 3 | 0 | 0 | 0 | 2 | 0 | user stories, SPMP | 5
2 | Alan | 11 | 10 | 1 | 0 - learning 1 - requirement analysis 5 - communication/management | 4 | 6 | 0 | 0 | 0 | 1 | 0 | UI mock ups, polish user stories, update SPMP | 10

## Christian
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Christian | 14 | 12 | 2 | 1 - requirement analysis 5 - attend group meeting, discuss. ... 6 - plan and set up infrastructure for SCM and software deployments to server | 0 | 2 |  |  |  | 2 | 8 | Set up repo layout, requirement analysis, begin learning technologies. | 12
2 | Christian | 22 | 21 | 1 | 0 - Learning required technologies for development 3 - Implementing reference code for back-end and configuring development server 5 - Communivations for and working on SCMP/SPMP | 6 |  |  | 12 |  | 3 |  | Begin developing services | 14

## Tandhy
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Tandhy | 9 | 7 | 2 | 5 - group meeting 1 - requirement analysis 0 - learning | 5 | 2 | 0 | 0 | 0 | 2 | 0 | 0 - learning 2 - design 5 - group meeting 6 - work on SQAP | 7
2 | Tandhy | 8 | 8 | 1 | 0 - learning 6 - SQAP documentation | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 - learning 6 - work on testing tools | 10